## Roadmap summary
DIGITAL COMMUNITY HEALTH ROADMAP FOR MALARIA, ANGOLA 2023-2025
PNCM
Roteiro Sobre Saude Comunitaria Digital em Angola, 2023-2024
Instruções: Baseado na discussão nas mesas de trabalho (área temática) identificar as actividades/procesos/etc. que precisam desenvolver-se para uma melhor integração da informação em saúde comunitária em DHIS2
No. | Activities Needed to Integrate Community Health into DHIS2 | Notes: Details of the activity that help you understand why you need it | Resources needed (e.g. 20 technicians trained in X, 30 computers, etc.) | Implementation schedule in 2023 |  |  |  | Implementation schedule 2024 |  |  |  | Implementation schedule in 2025 |  |  |  | Budget | Responsible for implementation | Other implementing partners
|  |  |  | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | T1 | T2 | T3 | T4 | USD
First Phase: Digitization at Municipal Health Directorate level
Insertion / Integration of Community Health Information in DHIS2
1 | Revision of the flowchart and paper tools for collecting information from the community agent to integration/insertion into DHIS2 | Identify the weaknesses of the current flowchart, review the ADECOS instruments and the aggregation and level of the HUs | 30 technicians (12 DPS + 2 PNCM + 2 GEPE + 2 GTI + 2 DNSP + 4 partners + 4 donors + 2 ADECOS), conference room rental, logistics (internet, projector, catering, laptop, transportation and telephone recharges), + 1 Consultant |  |  |  | X | X | [7 empty] | 25675 | DNSP/PNCM | PMI/USAID, PSI and Mentor, CHAI, WV
Management and Use of Community Information for Decision Making
2 | Development of dashboards (define levels of information use) | Develop panels at various levels and train technicians to use them | Technical assistance from a DHIS2 specialist |  |  |  |  | X | X | X | [5 empty] | 1013 | GTI-GEPE, PNCM, DNSP | PMI/USAID, PSI and Mentor, CHAI, WV
3 | Quarterly data analysis meetings with DMS and DPS joint activity | Data analysis for decision-making | 12 provinces, 44 municipalities, 4 times a year: conference room rental for 2 people per DMS and 2 people per DPS (malaria supervisors or statistician or epidemiological surveillance or director), plus DHIS2 official, logistics (internet, projector, catering, laptop, transportation) |  |  |  |  | X | X | X | X | X | X | X | X | 69300 | DPS, GEPE, PNCM | PMI/USAID, PSI and Mentor
4 | Monthly data analysis meetings at municipal level | Data analysis for decision-making | 44 municipalities * 10 months: conference room rental for 5 people per municipality (malaria supervisors, SSR, epidemiological surveillance, director, logistics (internet, projector, catering, laptop) |  |  |  |  | X | X | X | X | X | X | X | X | 41250 | DMS | Partners
5 | Creation and sharing of visualization bulletins created at all levels | Keeping decision-makers, technicians and partners at all levels informed | Technical assistance for preparation and automatic dissemination | [6 empty] | X | X | X | X | X | X | 1688 | GEPE-GTI, PNCM | PSI
Improving Data Quality
6 | Development of Standard Manuals on Data Collection, Review and Entry | To standardize data collection and reporting mechanisms | Technical assistance 1 specialist, 5 days, meeting room, catering for 10 people from MINSA and partners |  |  |  |  | X | X | [6 empty] | 6678 | DNSP/PNCM | PSI & Mentor, CHAI
7 | Routine supervision at the community level on data collection and aggregation | To check the quality, timeliness, accuracy and completeness of the data | 44 DMS supervisors: 1 day per month * 10 month |  |  |  |  | X | X | X | X | X | X | X | X | 27500 | DNSP/PNCM | PSI & Mentor, CHAI
8 | Routine supervision of data entry at the Health Unit and aggregation at the HU level | To assess the quality of the collection and aggregation of data from all the ADECOS attached to each HU to then send to the DMS | 308 HUs linked to ADECOS: each HU visited once a quarter (according to DHIS2) |  |  |  |  | X | X | X | X | X | X | X | X | 77000 | DMS | Partners
9 | Routine supervision of data entry in DHIS2 in the DMS and processing of information | To assess the quality of the collection and aggregation of data from all the ADECOS attached to each HU to then send to the DMS | 44 DMSs with ADECOS: each DMS visited once a month (10 months) |  |  |  |  | X | X | X | X | X | X | X | X | 27500 | DNSP/PNCM | PSI & Mentor
10 | Definition of validation rules and configuration in DHIS2 | To improve the quality of data entered in DHIS2. Have an alert when inconsistent data is entered. | 3 working days for the DHIS2 specialist and the central level team (GEPE-GTI, PNCM, DNDP) |  |  |  |  | X | X | [6 empty] | 1013 | DNSP/PNCM | PSI
11 | Configuration in DHIS2 of a mechanism for data approval prior to "publication" in DHIS2 | In the Health Unit to avoid bias and thus improve data quality | 1 working day for the DHIS2 specialist and the central level team (GEPE-GTI, PNCM, DNDP) |  |  |  |  | X | X | [6 empty] | 338
Ensuring Qualified Human Resources
12 | Training community agents in collecting, processing, sending information, etc. | To ensure that activities are implemented to the standards recommended by MINSA | 1,214 ADECOS |  |  |  |  | X | [7 empty] | 245643 | DNSP/PNCM | PSI & Mentor
13 | Training for supervisors of community agents (e.g. reviewing information, advising on filling in information, aggregating data, etc.) | To ensure that activities are implemented to the standards recommended by MINSA | 44 supervisores treinados para o efeito |  |  |  |  | X | [7 empty] | 8250 | DNSP/PNCM | PSI & Mentor
14 | Training of MINSA staff at each level who receive, process, and use information (define levels and type of training) | To ensure that activities are implemented to the standards recommended by MINSA | GEPE/GTI (Action already implemented) | [12 empty] | 0 | DNSP/PNCM | PSI & Mentor
15 | Training MINSA staff in data analysis and decision- making | To ensure that activities are implemented to the standards recommended by MINSA | GEPE/GTI (Action already implementaed) | [12 empty] | 0 | DNSP/PNCM | PSI & Mentor
Infrastructure / Software
16 | Smartphones | For communication between ADECOS and the HU and when necessary to send photos of the aggregate forms | Purchase of smartphones for 1,214 ADECOS | [5 empty] | X | X | [5 empty] | 121400 | DNSP/PNCM | Global Fund, WHO, UNDP, PSI & Mentor
17 | Data balance | Monthly data refill for ADECOS | Data refill for 12 months for 1,214 ADECOS | [6 empty] | X | X | X | X | X | X | 36420
18 | Tablets for HU to supervise ADECOS | Tablets for training and supervision of ADECOS in health units | 308 HU | [6 empty] | X | X |  |  |  |  | 46200
19 | Computers | Computer for the HUs that need to aggregate information from ADECOS | Computers for the Hus | [6 empty] | X | X |  |  |  |  | 246400
20 | Printer | Print monthly reports and send to the DMS | 308 HU | [6 empty] | X | X |  |  |  |  | 61600
Governance: regulations and leadership in administration
21 | Finalization / Dissemination of Community Health Policy | Finalization is the responsibility of the central level (MINSA). | 2-day meeting to disseminate and discuss Community Health Policies DNSP/PNCM and GEPE/GTI Technicians and Partners |  |  |  |  | X | X | [6 empty] | 525 | DNSP/PNCM | PSI, Mentor and others
22 | Review of Approval Policies and Procedures | Define hierarchies for user approval, modification of forms, electronic approval of data, harmonization of information | 4-day meeting of the technical team: DNSP/PNCM and GEPE/GTI Technicians and Partners | [5 empty] | X | X | [5 empty] | 1312.5
23 | Dissemination of Approval Policies and subsequent harmonization of this data | Define hierarchies for user approval, modification of forms, electronic approval of data, harmonization of information | Printing of 350 copies for central level and partners (30), DMS (12), HU (308) | [6 empty] | X | X |  |  |  |  | 8750
Evaluation of Roadmap Implementation
24 | Creation of a committee in charge of monitoring and drafting the Terms of Reference | Setting up the technical evaluation group, drawing up terms of reference | Catering for 3 days for 14 people |  |  |  |  | X | [7 empty] | 1312.5 | DNSP/PNCM | Global Fund, UNDP, PSI, Mentor and others
25 | Meetings (every 3 months) with MINSA and partners to review progress | Review roadmap progress, find solutions to possible problems | Room rental, catering (breakfast and lunch) | [5 empty] | X | X | X | X | X | X | X | 1750 | DNSP/PNCM | Global Fund, UNDP, PSI, Mentor and others
| Subtotal 1 | [14 empty] | 1058518
Second Phase: ADECOS digitalization using the DHIS2 data capture app
26 | Revision/Reconfiguration of the DHIS2 organizational tree | Indicate in DHIS2 where to receive the information from ADECOS | Technical assistance from 1 DHIS2 specialist for 5 days | [7 empty] | X | X |  |  |  | 1687.5 | GTI-GEPE | PSI-MENTOR, CHAI other partners
27 | Software (configuration of data capture in DHIS2 for the MINSA server) | Design and configuration of a template for entering data into the DHIS2 Data Capture application | Technical assistance from 1 DHIS2 specialist for 3 days | [7 empty] | X | X |  |  |  | 1012.5 | GTI-GEPE | PSI-MENTOR, CHAI other partners
28 | Infrastructure | Tablets for ADECOS to insert data directly in DHIS2 data capture application, internet balance | [10 empty] | X | X |  | 218520 | GTI-GEPE | USAID-PMI, Global Fund
29 | Training for ADECOS and supervisors on collecting information using data capture in DHIS2 | Training ADECOS (1,214) and supervisors (44) in the use of DHIS2 data capture | Conference room by province, catering, perdiems, etc. | [9 empty] | X | X |  | 486150 | GTI-GEPE | PSI-MENTOR, CHAI other partners
30 | Routine supervision at the community level (correct implementation of DHIS2 data capture app) | Supervision for the correct implementation of data collection | Monthly field visits: 44 supervisors * 10 visits per year | [9 empty] | X | X | X | 8250 | GTI-GEPE | PSI-MENTOR, CHAI other partners
31 | Revision/Creation of dashboards based on community information from DHIS2 data capture | Creation/Adaptation of dashboards for data analysis | Technical assistance 1 DHIS2 specialist | [10 empty] | X | X | 1687.5 | GTI-GEPE | PSI-MENTOR, CHAI other partners
32 | Expand server capacity and server maintenance (Bao System) given the substantial increase in the number of users | Due to the increase in users (1,214 ADECOS) the capacity of the BAO System server must be increased | Annual pay increase (2 years) | [10 empty] | X | X | 10000 | GTI-GEPE | USAID-PMI, Global Fund
| Subtotal 2 | [14 empty] | 727307.5
| Grand Total | [14 empty] | 1785825.5