## Product Development
eCHIS PRODUCT ROADMAP |  |  |  | (draft)
| Workstream | DETAILS | DETAILS | Completion date | Q3 2020 |  |  | Q4 2020 |  |  | Q1 2021 |  |  | Q2 2021 |  |  | Q3 2021 |  |  | Q4 2021 |  |  | Q1 2022 |  |  | Q2 2022 |  |  | Q3 2022 |  |  | Q4 2022
[5 empty] | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
| PROJECT WEEK: | Enter the date of the first Monday of each month --> |  |  | Q3 2020 JUL: 2; Q3 2020 AUG: 24; Q3 2020 SEP: 1; Q4 2020 OCT: 8; Q4 2020 NOV: 15; Q4 2020 DEC: 22; Q1 2021 JAN: 31; Q1 2021 FEB: 7; Q1 2021 MAR: 14; Q2 2021 APR: 1; Q2 2021 MAY: 8; Q2 2021 JUN: 15; Q3 2021 JUL: 22; Q3 2021 AUG: 29; Q3 2021 SEP: 6; Q4 2021 OCT: 13; Q4 2021 NOV: 20; Q4 2021 DEC: 27
| Family Folder + RMNCH Workflows | Family Folder 1.1 | Household, Client & Gote (register, edit, remove, delete), WDA & HDA management, HEP implementation & graduation, Household properties | bar: Q3 2020 JUL to Q4 2020 DEC
Family Folder 2.1
|  | RMNCH Release 1.1 | ANC, Pregnancy Outcome, PNC, Family Planning, EPI | bar: Q3 2020 JUL to Q4 2020 DEC
|  | RMNCH Release 2.1 | CNBC, ICCM, Nutrition | bar: Q1 2021 JAN to Q2 2021 JUN
| Reporting | Family Folder 1.1 | v1 mobile indicator reports | bar: Q3 2020 JUL to Q4 2020 DEC
|  | RMNCH Release 1.1 | v1 mobile indicator reports | bar: Q3 2020 JUL to Q4 2020 DEC
|  | RMNCH Release 2.1 | v1 mobile indicator reports | bar: Q1 2021 JAN to Q2 2021 JUN
|  | Web Reports v1 | v1 for RHB, WorHO, ZHD, HC | bar: Q1 2021 JAN to Q2 2021 JUN
| Biometric integration | Pilot work | bar: Q1 2021 MAR to Q2 2021 JUN
Scale up work | bar: Q3 2021 JUL to Q4 2021 DEC
| Performance & Usability | HEW & HC Referral App linkages | updates | bar: Q3 2021 JUL to Q4 2021 DEC
| Focal Person App | Improvements to functionality | scoping, updates | bar: Q3 2021 JUL to Q4 2021 DEC
| Additional Application Workflows | HIV | draft | bar: Q1 2022 JAN to Q4 2022 DEC
|  | TB & Leprosy | draft | bar: Q1 2022 JAN to Q4 2022 DEC
|  | NCDs | draft | bar: Q4 2022 JAN to Q4 2022 AUG
|  | NTDs | draft | bar: Q4 2022 JAN to Q4 2022 AUG
|  | Supply Chain | draft | bar: Q4 2022 JAN to Q4 2022 AUG
|  | CBHI | draft | bar: Q4 2022 JAN to Q4 2022 AUG
Urban & Pastoral settings

## Implementation
eCHIS IMPLEMENTATION ROADMAP |  |  |  | (draft)
| Workstream | DETAILS | DETAILS | Completion date | Q3 2021 |  |  | Q4 2021 |  |  | Q1 2022 |  |  | Q2 2022 |  |  | Q3 2022 |  |  | Q4 2022 |  |  | Q1 2023 |  |  | Q2 2023 |  |  | Q3 2023 |  |  | Q4 2023
[5 empty] | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
| PROJECT WEEK: | Enter the date of the first Monday of each month --> |  |  | 2 | 24 | 1 | 8 | 15 | 22 | 31 | 7 | 14 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27
| Family Folder + RMNCH Workflows | Family Folder 1.1 | to 1000HPs across 4 regions | bar: Q4 2021 DEC to Q1 2022 FEB
to additional SURE woredas | bar: Q1 2022 MAR to Q2 2022 MAY
Family Folder 2.1
|  | RMNCH Release 1.1 | to 1000 HPs across 4 regions | bar: Q4 2021 DEC to Q1 2022 FEB
to additional SURE woredas | bar: Q1 2022 MAR to Q2 2022 MAY
|  | RMNCH Release 2.1 | catchment area TBD | bar: Q3 2022 JUL to Q3 2022 SEP; Q1 2023 JAN to Q1 2023 MAR
| Reporting | Family Folder 1.1 | to 1000 HPs across 4 regions | bar: Q4 2021 DEC to Q1 2022 FEB
to additional CIFF woredas | bar: Q1 2022 MAR to Q2 2022 MAY
|  | RMNCH Release 1.1 | to 1000 HPs across 4 regions | bar: Q4 2021 DEC to Q1 2022 FEB
to additional CIFF woredas | bar: Q1 2022 MAR to Q2 2022 MAY
|  | RMNCH Release 2.1 | catchment area TBD | bar: Q3 2022 JUL to Q3 2022 SEP
|  | Web Reports v1 | catchment area TBD | bar: Q2 2022 APR to Q2 2022 MAY; Q3 2022 AUG to Q3 2022 SEP
| Biometric integration | Pilot | catchment area TBD | bar: Q2 2022 APR
|  | Scale up (phased) | catchment area TBD | bar: Q1 2023 JAN to Q1 2023 MAR; Q3 2023 JUL to Q3 2023 SEP
| Performance & Usability | HEW & HC Referral App linkages | length of training depedent on amount of UI changes | bar: Q1 2023 JAN to Q1 2023 MAR
| Focal Person App | Improvements to functionality | bar: Q1 2023 JAN to Q1 2023 MAR
| Additional Application Workflows | HIV | draft | bar: Q3 2023 JUL to Q3 2023 SEP
|  | TB and Malaria | draft | bar: Q3 2023 JUL to Q3 2023 SEP
|  | NCDs | draft
|  | NTDs | draft
|  | Supply Chain | draft
Urban & Pastoral settings